## Performance Targets
Quality and Clinical Care Directorate (QCCD) Performance Targets (PTs)
| PTs log for: |  |  |  |  | PTs STATUS
Enter name of Hospital
[6 empty] | Completed | 0
| Todays date: |  |  | 2018-03-22 |  | Not yet due | 83
[6 empty] | Late | 0
Note: Please ensure that the 'Entry Date' (i.e. date that PT is entered into the log) is completed, the 'Due Date' (i.e. date that the
PT is due for completion) is completed, and, when appropriate, the 'Completed Date' (i.e. date that PT has been fully implemented) is completed
Reference Number | Entry Date | Reference Name | Performance Area | Description of Performance Target | Due Date | Completed Date | PT Status | Comments
1 | 2010-02-01 | Framework | Communication and Consultation | The organisation has a documented policy outlining arrangements for conducting a stakeholder analysis and for ensuring that the analysis is maintained up-to-date | 31/06/2010 |  | Not yet due
2 | 2010-02-01 |  |  | The organisation has carried out a stakeholder analysis to identify all internal and external stakeholders | 31/06/2010 |  | Not yet due
3 | 2010-02-01 |  | Accountability | The organisation has a document which outlines clear roles, responsibilities and reporting relationships at all levels of the service from front line staff up to the most senior manager in the organisation or to the board | 31/06/2010 |  | Not yet due
4 | 2010-02-01 |  |  | The board of the service/management team regularly receives information regarding specific outcomes relating to quality and safety of clinical care, in order to measure and monitor the management of quality and safety of clinical care. | 31/06/2010 |  | Not yet due
5 | 2010-02-01 |  |  | The manager/CEO reports regularly on specific healthcare related outcomes to the board (voluntary) of the service or to the appropriate management level (ISA/Network/RDO) | 31/06/2010 |  | Not yet due
6 | 2010-02-01 |  |  | The organisation has a clinical governance (or appropriate committee) in place, which is chaired by the clinical director. The terms of reference of this committee are in line with the HSE accountability guidance document (2010) | 31/06/2010 |  | Not yet due
7 | 2010-02-01 |  |  | The roles of the manager/CEO and Clinical Director are separate (the manager/CEO leads and manages the organisation and the Clinical Director is accountable to the manager/CEO for clinical outcomes and the quality and safety of patient care in the healthc | 31/06/2010 |  | Not yet due
8 | 2010-02-01 |  |  | The organisation has reviewed its committees and other formally established groups in line with the HSE accountability guidance document (2010) | 31/06/2010 |  | Not yet due
9 | 2010-02-01 |  |  | The healthcare organisation has a clear policy on when and how it consults and involves staff and their representatives in decision making. | 31/09/2010 |  | Not yet due
10 | 2010-02-01 |  |  | The organisation has a policy to ensure that at all times during an episode of care, it is clearly identified and documented who is the accountable clinician responsible for the patient | 31/06/2010 |  | Not yet due
11 | 2010-02-01 |  | Capacity and capability | Quality, safety and risk management/clinical governance matters are standing agenda items at various regular management meetings (board/management team/clinical directorate/departmental) | 31/06/2010 |  | Not yet due
12 | 2010-02-01 |  |  | The organisation has set aside specific financial resources for achieving defined quality, safety and risk management goals | 31/06/2010 |  | Not yet due
13 | 2010-02-01 |  |  | The organisation has a ‘resource matrix’ which sets out all expert resources available at different levels to implement effective quality, safety and risk management systems | 31/06/2010 |  | Not yet due
14 | 2010-02-01 |  |  | The organisation has a documented analysis of information, instruction and training needs for quality, safety and risk management | 31/09/2010 |  | Not yet due
15 | 2010-02-01 |  | PPPGs | The organisation operates a standardised document control process for all policies, procedures, protocols and guidelines | 31/06/2010 |  | Not yet due
16 | 2010-02-01 |  | Monitoring and review | The organisation has completed the annual Framework self-assessment and identified areas for improvement. | 31/06/2010 |  | Not yet due
17 | 2010-02-01 |  |  | The self-assessment results and associated list of quality improvement plans (QIPs) have been reviewed and signed-off by the clinical governance (or appropriate) committee | 31/06/2010 |  | Not yet due
18 | 2010-02-01 |  | Assurance | The organisation has constructed a matrix of all actual sources of assurance available from within and outside the organisation and determined, based on the organisation’s risk profile, whether it is felt that sufficient assurance exists, or whether there or whether there are gaps in assurance | 31/06/2010 |  | Not yet due
19 | 2010-02-01 |  |  | The recommendations from Healthcare Audits (Level 2) and associated list of actions/quality improvement plans (QIPs) have been reviewed and signed-off by the clinical governance (or appropriate) committee | 31/06/2010 |  | Not yet due | Report on this PT for each quarter
20 | 2010-02-01 |  | Clinical effectiveness and audit | The organisation has developed and/or implemented an Annual Clinical Audit Forward Plan as part of its annual planning and delivery cycle for clinical audit activities. This Plan should reflect the national, organisational, team and individual audit requirements on the facility. It should be the responsibility of the Clinical Director, with accountability for safety and quality at senior level, to ensure that the Plan is developed and implemented with effective clinical engagement and reported to the senior management team of the facility | 31/06/2010 |  | Not yet due
21 | 2010-02-01 |  | Patient/Service user and public/community involvement | The organisation has carried out a consultation at local level with service users on the draft National Guidelines—The HSE and You (A National Patients Charter) | 31/06/2010 |  | Not yet due
22 | 2010-02-01 |  |  | The organisation has developed an implementation plan for how the guidelines will be implemented at local level and communicated to both staff and service users | 31/06/2010 |  | Not yet due
23 | 2010-02-01 |  |  | The organisation has a plan in place to ensure all new patient/service user information is developed in line with the checklist for producing effective service user health information (see guidance document for service user involvement) | 31/06/2010 |  | Not yet due
24 | 2010-02-01 |  |  | The organisation has a plan in place to ensure that all patient/service user information which is due for review in 2010 is reviewed in line with the checklist for in line with the checklist for producing effective service user health information (see HSE Guidance document for service user involvement 2010) | 31/06/2010 |  | Not yet due
25 | 2010-02-01 |  |  | The organisation has disseminated a ‘Quick Guide to user involvement for frontline staff working with children and young people | 31/06/2010 |  | Not yet due
26 | 2010-02-01 |  |  | The organisation has a plan in place to monitor and evaluate implementation of this guide | 31/09/2010 |  | Not yet due
27 | 2010-02-01 |  |  | Posters about Your Service Your Say are visible and service users have access to leaflets and information about giving feedback | 31/06/2010 |  | Not yet due
28 | 2010-02-01 |  |  | The organisation has selected a month in 2010 to organise a promotional campaign on “Your Service Your Say” HSE Service User feedback (conducted) | 31/06/2010 |  | Not yet due | Report on this PT for each quarter
29 | 2010-02-01 |  |  | The organisation has a policy in place to capture the views of service users on their experience of services (e.g. patient satisfaction surveys) | 31/06/2010 |  | Not yet due
30 | 2010-02-01 |  |  | Feedback received from service users is regularly reviewed and taken into account for service planning in 2010 and quality improvement initiatives at local level | 31/06/2010 |  | Not yet due
31 | 2010-02-01 |  |  | The organisation has a policy in place to ensure that service users’ know what changes and improvements have been made to services as a result of their feedback | 31/06/2010 |  | Not yet due
32 | 2010-02-01 |  |  | The organisation complies with the HSE policy for the Management of Complaints under Part 9 of the Health act (2007) | 31/06/2010 |  | Not yet due | Report on this PT for each quarter
33 | 2010-02-01 |  |  | The organisation has mapped out what existing structures are in place at healthcare organisation level to involve service users in planning, design and evaluation of services | 31/06/2010 |  | Not yet due
34 | 2010-02-01 |  |  | The organisation has identified two or more service users who are members of the clinical governance committee (or appropriate committee) | 31/06/2010 |  | Not yet due
35 | 2010-02-01 |  |  | The organisation has developed a plan to ensure the integration and active involvement of service users in planning, design, delivery and evaluation of services (e.g. service user panels) | 31/06/2010 |  | Not yet due
36 | 2010-02-01 |  | Risk Management and Patient Safety | Risk registers are in place at all levels in the organisation, i.e. at departmental or service level and up to senior management level | 31/06/2010 |  | Not yet due | Report on this PT for each quarter
37 | 2010-02-01 |  |  | The organisation has a system in place to ensure that all incidents, complaints and claims are properly recorded; reported to management; managed in accordance with an agreed policy; rated according to impact; reviewed where appropriate to determine controls | 31/09/2010 |  | Not yet due
38 | 2010-02-01 |  | Staffing and staff management | The organisation has arrangements in place to ensure appropriate recruitment procedures and induction training for staff appropriate to their roles and responsibilities | 31/09/2010 |  | Not yet due
39 | 2010-02-01 |  | Service improvement | The organisation has identified quality priorities for 2010 which are in line with the HSEs corporate plan and has a structured programme in place to support continuous quality improvement across all services. | 31/06/2010 |  | Not yet due
40 | 2010-02-01 |  | Learning and sharing information | The organisation has a structured programme in place to ensure that it routinely learns from incidents occurring within and outside the organisation | 31/06/2010 |  | Not yet due
41 | 2010-02-01 |  | Serious Incident Management | The organisation adheres to to PPPGs for management of serious incidents | 31/06/2010 |  | Not yet due | Report on this PT for each quarter
42 | 2010-02-01 | National HSE Standards | Healthcare Records | The organisation has completed the annual healthcare records self-assessment and identified areas for improvement. | 31/06/2010 |  | Not yet due
43 | 2010-02-01 |  |  | The self-assessment results and associated list of quality improvement plans (QIPs) have been reviewed and signed-off by the clinical governance (or appropriate) committee | 31/06/2010 |  | Not yet due
44 | 2010-02-01 |  |  | The organisation has an appropriate procedure in place to identify duplicate and temporary charts | 31/06/2010 |  | Not yet due
45 | 2010-02-01 |  |  | The organisation has an agreed service level agreement (SLA) in place for healthcare records retrieval | 31/06/2010 |  | Not yet due
46 | 2010-02-01 |  |  | The organisation has a formal appraisal system in place to monitor staff performance and to identify individual training needs in relation to healthcare records management | 31/06/2010 |  | Not yet due
47 | 2010-02-01 |  | Discharge Planning | The organisation has completed the annual discharge planning self-assessment and identified areas for improvement. | 31/06/2010 |  | Not yet due
48 | 2010-02-01 |  |  | The self-assessment results and associated list of quality improvement plans (QIPs) have been reviewed and signed-off by the clinical governance (or appropriate) committee | 31/06/2010 |  | Not yet due
49 | 2010-02-01 |  |  | The organisation has a policy in place to ensure that patient assessment will begin either prior to admission or at first presentation to the hospital | 31/06/2010 |  | Not yet due
50 | 2010-02-01 |  |  | The organisation has a policy in place to ensure that within one hour of patient admission to the ward, appropriate and competent Nurses (or HSCPs/Others) are identified and assigned to actively manage the patient pathway of care | 31/06/2010 |  | Not yet due
51 | 2010-02-01 |  |  | The organisation has a policy in place to ensure that each patient has a documented length of stay | 31/06/2010 |  | Not yet due
52 | 2010-02-01 |  |  | The organisation has a policy in place to ensure that transport arrangements are confirmed 24 hours before discharge | 31/06/2010 |  | Not yet due
53 | 2010-02-01 |  |  | The organisation has a policy in place to ensure that PCCC service providers, as appropriate, are informed of the planned discharge date as soon as possible, and at least two days prior to patient discharge (for patients who are in-patients for five days or longer) to enable them to plan the necessary post-hospital service commencement | 31/06/2010 |  | Not yet due
54 | 2010-02-01 |  |  | The organisation has a policy in place to ensure that each patient discharge is effected (i.e. hospital bed becomes available for patient use) no later than 12 noon on the day of discharge. This includes completion of all necessary discharge procedures, documentation of the time of discharge in the healthcare record and communication with patients, carers and other healthcare providers (where relevant) | 31/06/2010 |  | Not yet due
55 | 2010-02-01 |  | Decontamination of RIMD | The organisation has completed the annual decontamination self-assessment and identified areas for improvement. | 2010-12-31 |  | Not yet due
56 | 2010-02-01 |  |  | The self-assessment results and associated list of quality improvement plans (QIPs) have been reviewed and signed-off by the clinical governance (or appropriate) committee | 2010-12-31 |  | Not yet due
57 | 2010-02-01 |  |  | Each decontamiation unit is designed to allow segregation of ‘dirty’ and ‘clean’ activities | 31/06/2010 |  | Not yet due
58 | 2010-02-01 |  |  | Manual washing is used only when required by manufacturers’ instructions or as a pre-treatment prior to reprocessing through a Washer-Disinfector | 31/06/2010 |  | Not yet due
59 | 2010-02-01 |  |  | Separate sinks for washing and rinsing RIMD are provided | 31/09/2010 |  | Not yet due
60 | 2010-02-01 |  |  | Each decontamination unit has a person appointed with responsibility for operational management of the unit, which may be in addition to other duties | 31/06/2010 |  | Not yet due
61 | 2010-02-01 |  |  | Maintenance and test personnel are available and suitably qualified for the decontamination equipment in use | 31/06/2010 |  | Not yet due
62 | 2010-02-01 |  |  | The organisation has a specialist group in place to consider the procurement of RIMD | 31/06/2010 |  | Not yet due
63 | 2010-02-01 |  |  | All stages of the decontamination process are clearly defined, documented, controlled and recorded | 31/06/2010 |  | Not yet due
64 | 2010-02-01 |  |  | All RIMD sets are traced through the decontamination process to the patient | 31/09/2010 |  | Not yet due
65 | 2010-02-01 |  |  | All product released from the decontamination unit is labelled with a clear indication of the pack contents, the expiry date and a unique number which shall be used to trace the decontamination processes to which the device was subjected | 31/06/2010 |  | Not yet due
66 | 2010-02-01 |  | HCAI | The organisation has completed the annual decontamination self-assessment and identified areas for improvement | 2010-12-31 |  | Not yet due
67 | 2010-02-01 |  |  | The self-assessment results and associated list of quality improvement plans (QIPs) have been reviewed and signed-off by the clinical governance (or appropriate) committee | 2010-12-31 |  | Not yet due
68 | 2010-02-01 |  |  | Resources are allocated to provide a safe, effective and efficient service to prevent and control HCAIs. The resources allocated are based on a needs analysis and evidence-based best practice | 31/06/2010 |  | Not yet due
69 | 2010-02-01 |  |  | Contracted external services relating to the prevention and control of HCAIs, including hygiene services, are effectively and efficiently governed, monitored and performance managed | 31/06/2010 |  | Not yet due
70 | 2010-02-01 |  |  | A multidisciplinary Infection Prevention and Control committee is in place which reflects the size, complexity and specialties of the service. | 31/06/2010 |  | Not yet due
71 | 2010-02-01 |  |  | There is a programme to prevent and control HCAIs which reflects the size, complexity and specialties of the service | 31/06/2010 |  | Not yet due
72 | 2010-02-01 |  |  | The design and layout of the facility is based on a needs assessment which reflects the size, complexity and specialties of the service provided including facilities in the primary and community care setting. The design and layout complies with relevant legislation and evidence | 31/09/2010 |  | Not yet due
73 | 2010-02-01 |  |  | All staff receive mandatory theoretical and practical training in the prevention and control of HCAIs. This training is delivered during orientation/induction, with regular updates, is job/role specific and attendance is audited. There is a system in place to flag non-attendees | 31/06/2010 |  | Not yet due
74 | 2010-02-01 |  |  | A communication strategy is in place to ensure all service users, relatives, carers, visitors and staff are made aware of the importance of the prevention, control and reduction of HCAIs | 31/06/2010 |  | Not yet due
75 | 2010-02-01 |  |  | Service users and their relatives/carers/visitors are informed (verbally and in writing) that they can ask staff if they have performed hand hygiene before attending to them and also request staff to practice hand hygiene. | 31/06/2010 |  | Not yet due
76 | 2010-02-01 |  | Hygiene | The organisation has completed the annual hygiene self-assessment and identified areas for improvement. | 2010-12-31 |  | Not yet due
77 | 2010-02-01 |  |  | The self-assessment results and associated list of quality improvement plans (QIPs) have been reviewed and signed-off by the clinical governance (or appropriate) committee | 2010-12-31 |  | Not yet due
78 | 2010-02-01 |  |  | The quality of hygiene services is regularly monitored and evaluated and this information is used to improve the service provided | 31/06/2010 |  | Not yet due
79 | 2010-02-01 |  | Health and Safety | The organisation has completed the annual health and safety self-assessment and identified areas for improvement. | 31/06/2010 |  | Not yet due
80 | 2010-02-01 |  |  | The self-assessment results and associated list of quality improvement plans (QIPs) have been reviewed and signed-off by the clinical governance (or appropriate) committee | 31/06/2010 |  | Not yet due
81 | 2010-02-01 |  |  | The organisation has a documented safety and health policy | 31/06/2010 |  | Not yet due
82 | 2010-02-01 |  |  | Organisation has in place up-to-date safety statement, in accordance with requirements | 31/06/2010 |  | Not yet due
83 | 2010-02-01 |  |  | The content of the safety statement is brought to the attention of all employees at least annually | 31/06/2010 |  | Not yet due
Note on E7: This date is entered automatically from the computer's system clock.

## Framework QIPs
NHO Framework for Integrated Quality, Safety and Risk Management
| QIPs LOG FOR: | [5 empty] | QIPs STATUS
Enter name of hospital etc.
|  |  |  | TODAY'S DATE: | 2010-03-03 |  | Completed | 0
[7 empty] | Not yet due | 0
[7 empty] | Late | 0
Note: Please ensure you enter the 'Entry Date' (i.e. date that QIP is entered into the log), 'Due Date' (i.e. date that the
QIP is due for completion), and, when appropriate, the 'Completed Date' (i.e. date that QIP has been fully implemented).
Number | Entry Date | Standard | Criterion | Description of Quality Improvement Plan (QIP) | Responsible Person | Due Date | Completed Date | QIP Status | Comments
1 | 03.03.2010 | A | 1 | Staff Survey to be further developed | Ian Maguire H.R. Manager | Q4 2010 |  | Not yet due
2 | 03.03.2010 | A | 1 | Further Patient participation on committees | Senior Management which includes Ann brennan Quality Manager & Bernie Farrelly | Q4 2010 |  | Not yet due
3 | 03.03.2010 | A | 3 | Audit of Communication Policy | Ann Brennan | Q4 2010 |  | Not yet due
4 | 03.03.2010 | A | 4 | Formalise follow up with staff in regards to Patient Satisfaction Survey | Fran Campbell | Q4 2010 |  | Not yet due
5 | 03.03.2010 | C | 1 | Patient tracer education to be provided to more clinical staff and further patient tracers to be carried out. Continuation of root causes analysis Near miss reviews for educational potential | Quality Manager Ann Brennan Director of Nursing Josephine Barrett Risk Manager Bernie Farrelly | Q4 2010 |  | Not yet due
6 | 03.03.2010 | C | 5 | Staff Questionnaire to be developed to ensure educational needs are being met. New database system to record and monitor training attended and when next due. | Ian Maguire / Fran Campbell / ICT | Q4 2010 |  | Not yet due
7 | 03.03.2010 | D | 2 | Link to HSE FOR Policies & Procedures that need future development Ongoing education to staff on the development and auditing of policies | Ann Brennan / Fran Campbell | Q4 2010 |  | Not yet due
8 | 03.03.2010 | E | 2 | Current KPI's agrees by SVUHG Exceutive Committee ongoing. Development of Further Clinical KPI's | Ann Brennan / Seamus Murtagh / Ken Bale / Ian Maguir Fran Campbell | Q4 2010 |  | Not yet due
9 | 03.03.2010 | E | 3 | Ongoing in Conjunction with SVUHG Site specific KPI's to be developed | Ann Brennan / Seamus Murtagh / Ken Bale / Ian Maguir Fran Campbell | Q4 2010 |  | Not yet due
10 | 03.03.2010 | G | 1 | Ongoing education of staff in audit | Ann Brennan / Ian Calahan / Fran Campbell | Q4 2010 |  | Not yet due
11 | 03.03.2010 | G | 2 | Senior Manager to be invited onto Audit Committee | Fran Campbell / Ann Brennan | Q2 2010 |  | Not yet due
12 | 03.03.2010 | G | 5 | Inclusion of Allied Health Professionals in Audit Process | Ann Brennan, Frances Campbell | Q4 2010 |  | Not yet due
13 | 03.03.2010 | G | 6 | Ongoing re-audit of current policies and procedures to ensure clinical effectiveness | Ann Brennan, Bernie Farrelly, Frances Campbell | Q4 2010 |  | Not yet due
14 | 03.03.2010 | H | 1 | Clinical Patient Education and family involvement document developed and in use plans to expand to all disciplines in 2010 | Fran Campbell | Q4 2010 |  | Not yet due
15 | 03.03.2010 | H | 3 | Clinical Specialist areas to get feedback from service users re patient information leaflets already in place | Fran Campbell / Clinical Nurse Specialists | Q4 2010 |  | Not yet due
16 | 03.03.2010 | H | 5 | Ongoing review for patient service needs | Ann Brennan / Bernie Farrelly | Q4 2010 |  | Not yet due
17 | 03.03.2010 | I | 1 | Development of departmental specific Risk Registers | Bernie Farrelly | Q4 2010 |  | Not yet due
18 | 03.03.2010 | I | 2 | Development of departmental specific Risk Registers | Bernie Farrelly | Q4 2010 |  | Not yet due
19 | 03.03.2010 | I | 3 | Development of departmental specific Risk Registers | Bernie Farrelly | Q4 2010 |  | Not yet due
20 | 03.03.2010 | I | 4 | Development of departmental specific Risk Registers | Bernie Farrelly | Q4 2010 |  | Not yet due
21 | 03.03.2010 | I | 5 | Annual self assessment with HAS Audit Tool | Bernie Farrelly | Q4 2010 |  | Not yet due
22 | 03.03.2010 | M | 1 | Local clinical KPI's to be developed | Fran Campbell | Q4 2010
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
Note on F6: This date is entered automatically from the computer's system clock.

## HSA QIP
Health & Safety Audit (HSA)
| QIPs LOG FOR: | [5 empty] | QIPs STATUS
Enter name of hospital etc.
|  |  |  | TODAY'S DATE: | 2018-03-22 |  | Completed | 18
[7 empty] | Not yet due | 14
[7 empty] | Late | 0
Note: Please ensure you enter the 'Entry Date' (i.e. date that QIP is entered into the log), 'Due Date' (i.e. date that the
QIP is due for completion), and, when appropriate, the 'Completed Date' (i.e. date that QIP has been fully implemented).
No. | Entry Date | Standard | Criterion | Description of Quality Improvement Plan (QIP) | Responsible Person | Due Date | Completed Date | QIP Status | Comments
1 | 09.11.09 | 1 | 1.7 | Formalised action plan for Heads of Department | Bernie Farrelly | Q4 2010 |  | Not yet due
2 | 09.11.09 | 1 | 1.9 | Indivudual budget for Health ans Safety Resources | Ken Bale | Q4 2010 |  | Not yet due | On hold due to overall bugetary restraints
3 | 09.11.09 | 2 | 2.4 | Formalised Audit of Safety Statement | Bernie Farrelly | Q2 2010 | Ongoing | Completed
4 | 09.11.09 | 3 | 3.1 | Arrange with IT Dept to avail of Barbour Index within budetary constraints | Cathal Prendergast | Q2 2010 | 01.8.2010 | Completed | Due to finacial constraints not availing of same update received through Dublin Hospitals Health & Safety Advisory Group
5 | 09.11.09 | 3 | 3.2 | Regular review to be commenced in accordance with Barbour Index | Bernie Farrelly | Q3 2010 | 01.08.2010 | Completed | As above
6 | 09.11.09 | 4 | 4.2 | Currently in correspondance with HSE in regards to Major Disaster Planning | Bernie Farrelly | Q3 2010 | Ongoing | Completed | Attended Emergency Planning Workshop in Sept 2010
7 | 09.11.09 | 4 | 4.4 | Discuss with Occupational Health Department if additional First Aiders are required within organisation | Bernie Farrelly | Q1 2010 | 21.03.2010 | Completed | Not applicable incidents referred to A&E 8am-8pm and nursing adminstration after hours
8 | 09.11.09 | 5 | 5.4 | Formalised Audit of H&S Consultation process | Bernie Farrelly | Q4 2010 |  | Not yet due | Not yet formalised
9 | 10.11.09 | 5 | 5.10.Review Terms of Reference |  | Bernie Farrelly | Q1 2010 | 10.02.2010 | Completed
10 | 10.11.09 | 5 | 5.12 | Election process for Safety Reprensenative | Bernie Farrelly | Q4 2011 |  | Not yet due | Will review nest year as finacial constraints on out of house courses, curent safety represenative remains in post.
10 | 10.11.09 | 7 | 7.11 | Centralisation of all training records | Cathal Prendergast | Q2 2010 | Ongoing | Completed | New database under construction
11 | 10.11.09 | 9 | 9.4 | Development of Departmental Risk Registers as well as Hospital wide Risk Register | Bernie Farrelly | Q2 2010 | Ongoing | Completed
12 | 10.11.09 | 9 | 9.5 | In-house training on the management of adverse events | Bernie Farrelly | Q4 2010 |  | Not yet due | To be formalised
13 | 10.11.09 | 9 | 9.6 | Develop further feeback channels for service users in relation to Health and Safety Issues | Bernie Farrelly | Q4 2010 |  | Not yet due
14 | 10.11.09 | 10 | 10.3 | Liasie with Infection Control on risk assessments during builing Projects | Bernie Farrelly / Siobhan Mc Caffery | Ongoing | Ongoing | Completed
15 | 10.11.09 | 10 | 10.6 | Development of plan for designated pedestrian route | Bernie Farrelly | Q4 2010 | Q4 2011 | Completed | Will be reviewed following completion of all building projects
16 | 10.11.09 | 10 | 10.7 | Develop specific Health and Safety Feedback form for Service Users and Public | Bernie Farrelly | Q4 2010 |  | Not yet due | To be formalised
17 | 18.11.09 | 11 | 11.2 | Review of risk assessment with on site contractors | Bernie Farrelly / Siobhan Mc Caffery | Ongoing | Ongoing | Completed
18 | 18.11.09 | 11 | 11.11 | Contractor Safety Statement to be brought to the attention of staff that may be affected by their activities | Bernie Farrelly | Ongoing | Ongoing | Completed
19 | 18.11.09 | 11 | 11.2 | Health and Safety Folder for Contractors to be created | Bernie Farrelly | Q1 2010 | 010.02.2010 | Completed
20 | 23.11.09 | 13 | 13.9 | Formalised lines of accountability between occupational health and organisation | Anne Mc Fadden | Q4 2010 | Ongoing | Completed
21 | 18.11.09 | 14 | 14.2 | In conjunction with HSE further work to be done on Major Disaster Plan. | Bernie Farrelly | Q4 2010 | Ongoing | Completed
22 | 18.11.09 | 14 | 14.5 | Destop exercise for senior management on control and command | Bernie Farrelly | Q2 2011 |  | Not yet due | To be arranged for 2011
23 | 18.11.09 | 14 | 14.8 | Liasie with local fire prevention station on response times | Bernie Farrelly | Q4 2010 |  | Not yet due
24 | 18.11.09 | 15 | 15.5 | Trend analysis to be completed on injury / ill health absences | Occ Health & HR | Q4 2010 | Ongoing | Completed
25 | 18.11.09 | 16 | 16.1 | Local KPI with a view to Health and Safety to be developed. | Bernie Farrelly | Q4 2010 |  | Not yet due | To be formalised
26 | 18.11.09 | 16 | 16.3 | Local KPI with a view to Health and Safety to be developed. | Bernie Farrelly | Q4 2010 |  | Not yet due | To be formalised
27 | 18.11.09 | 16 | 16.4 | Local KPI with a view to Health and Safety to be developed. | Bernie Farrelly | Q4 2010 |  | Not yet due | To be formalised
28 | 18.11.09 | 16 | 16.4 | Local KPI with a view to Health and Safety to be developed. | Bernie Farrelly | Q4 2010 |  | Not yet due | To be formalised
29 | 18.11.09 | 17 | 17.7 | Local KPI with a view to Health and Safety to be developed. | Bernie Farrelly | Q4 2010 |  | Not yet due | To be formalised
30 | 18.11.09 | 18 | 18.2 | Annual self assessment of HAS audit | Bernie Farrelly | Q4 2010 | Ongoing | Completed
31 | 18.11.09 | 18 | 18.3 | Further training on preforming audits to be carried out | Fran Campbell | Ongoing | Ongoing | Completed
32
33
34
Note on F6: This date is entered automatically from the computer's system clock.

## Healthcare Records QIPs
NHO Healthcare Records Management Self-assessment
| QIPS LOG FOR: |  |  | St. Michael's Hospital |  |  | QIPs STATUS
Enter name of hospital
|  |  |  | TODAY'S DATE: | 2018-03-22 |  | Completed | 7
[7 empty] | Not yet due | 23
[7 empty] | Late | 0
Note: Please ensure you enter the 'Entry Date' (i.e. date that QIP is entered into the log), 'Due Date' (i.e. date that the
QIP is due for completion), and, when appropriate, the 'Completed Date' (i.e. date that QIP has been fully implemented).
No. | Entry Date | Standard | Criterion | Description of QIP | Responsible Person | Due Date | Completed Date | QIP Status | Comments
|  | 1 | 3.1 | Insert in relevant job descriptions their responsibility for HC R | Ann Brennan | Q 2 09
1 | 27.10.09 | 1 | 3.3 | Broaden reports from Patient Services Officer to Risk Management Committee | Oliver Cunningham | Quarter 4 09 |  | Not yet due
2 | 27.10.09 | 1 | 3.4 | Ensure Healthcare Records is a regular item on all relevant committees | Ann Brennan | Quarter 1 2010 |  | Not yet due
3 | 27.10.0 | 1 | 3.4 | Ensure Healthcare Records is a regular item on all relevant committees | Ann Brennan | Quarter 1 2010 |  | Not yet due
4 | 27.10.09 | 1 | 3.13 | Itemised expenditure report needed | Ken Bale | Quarter 4 2010 |  | Not yet due
5 | 27.10.09 | 2 | 3.2 | Review lighting arrangement with Hospital Electrician to determine appropiate solution | Ann Brennan / Conor Neiland |  | 01.06.09 | Completed
6 | 27.10.09 | 2 | 3.3 | Erogoniomically improved workstation in OPD department completed | Ann Brennan |  | 2008-11-01 | Completed
7 | 27.10.09 | 2 | 3.4 | Infrastructure to be looked at within budgetary constraints | Ann Brennan / Ken Bale / Seamus Murtagh | Quarter 4 2010 |  | Not yet due
8 | 27.10.09 | 2 | 3.5 | As for Criteria 2.3.4 | Ann Brennan / Ken Bale / Seamus Murtagh | Quarter 4 2010 |  | Not yet due
9 | 27.10.09 | 2 | 3.7 | Locked trolleys ordered to house Healthcare Reocrds for all wards | Ann Brennan |  | 2009-09-01 | Completed
10 | 27.10.09 | 2 | 3.10. | Infrastructure to be looked at within budgetary constraints | Ken Bale / Seamus Murtagh / Ann Brennan | Quarter 4 2010 |  | Not yet due
11 | 27.10.09 | 2 | 3.11 | Infrastructure to be looked at within budgetary constraints | Ken Bale / Seamus Murtagh / Ann Brennan | Quarter 4 2010 |  | Not yet due
12 | 27.10.09 | 2 | 3.13 | More Fire fighting equipment now in place in secondary filing areas | Bernie Farrelly |  | 2008-02-01 | Completed
13 | 27.10.09 | 2 | 3.15 | Archive storage to be looked at in 2011 | Ann Brennan / Ken Bale | Quarter 4 2011 |  | Not yet due
14 | 27.10.09 | 2 | 3.18 | Significant resource required | Seamus Murtagh / Ken Bale / Ann Brennan | Quarter 4 2011 |  | Not yet due
15 | 27.10.09 | 2 | 3.22 | Risk Register currently being undertaken by Hospital | Bernie Farrelly / Ann Brennan | Quarter 4 2009 |  | Not yet due
16 | 27.10.09 | 3 | 3.6 | Electronical tracking system being looked at to replaced manual system | Ann Brennan / Cathal Prendergast | Quarter 4 2011 |  | Not yet due | Ann Brennan
| 27/10.09 | 4 | 4 | Implement Group Training documentt for clinicians on 'how to document' when passed by medical board |  |  | Quarter 2 2010
17 | 27.10.09 | 4 | 3.2 | Copies of departmental training to be kept on HR files | Ian Maguire | Quarter 4 2010 |  | Not yet due
| 2009-11-02 | 4 | 4.3.2 | Introduce new question on staff induction form to include attendance at Quality Healtncare Record keeping course |  |  | 2009-11-01
18 | 27.10.09 | 4 | 3.5 | Needs analysis training to be further developed, no programme in place at present | Ian Maguire | Quarter 4 2010 |  | Not yet due
19 | 27.10.09 | 4 | 3.6 | Formalisation of process needs to be put in place | Ann Brennan | Quarter 2 2010
20 | 27.10.09 | 4 | 3.7 | Formal process need to be put in place to replace current informal process | Ian Maguire | Quarter 3 2010
21 | 27.10.09 | 5 | 3.6 | policy number and revision date to be put on all policies and procedures | Ann Brennan | Q2
22 | 27.10.09 | 5 | 3.12 | Key control to be developed in the future | Ian Maguire | quarter 4 2011
23 | 27.10.09 | 5 | 3.13 | To be developed in line with SVUH group policy | Cathal PrendergastQuarter 4 2010 |  |  |  | Not yet due
24 | 27.10.09 | 6 | 6.3.1 | Plan in place to introduce computerised emergency department link to patient administration system | Seamus Murtagh / Ken Bale / Ann Brennan |  |  |  | Not yet due
25 | 27.10.09 | 6 | 6.3.2 | Plan in place to introduce computerised emergency department link to patient administration system |  |  |  | Quarter 1 2008 | Completed
26 | 27.10.09 | 6 | 6.3.3 | Non clinical audit now carried out on a regular basis, plan to introduce clinical audit of Healthcare Record twice yearly | Ann Brennan | Quarter12010 |  |  | Not yet due
27 | 27.10.09 | 6 | 6.3.10 | Further training needed. Combined SVUHG procedures in place |  |  | Quarter 2 2009
28 | 27.10.09 | 6 | 6.3.13 | Separate numbering system in Emergency Department. Plan in place to introduce computerised emergency department link to patient administration system |  | Quarter 4 2010
| 27.10.09 | 8 | 8.3.1 | Audit committee only in place since January 2008. Staff knowledge and expertise policies prodecures and guidelines in place, more work needs to be done on audit reporting. (ongoing) |  | Ann Brennan
29 | 27.10.09 | 8 | 8.3.2 | Audit Committee to write to Allied Health professionals to invite them to attend next audit committee to plan audits for 2010 |  |  | Ann Brennan | Completed
30 | 27.10.09 | 8 | 8.3.4 | More structures to be put in place via the audit committee for ensuring remedial action is undertaken | Ann Brennan | Quarter 1 2010 |  | Not yet due
31 | 27.10.09 | 8 | 8.3.5 | More structures to be put in place via the audit committee for ensuring remidial action is undertaken | Ann Brennan | Quarter 1 2010 |  | Not yet due
32 | 27.10.09 | 8 | 8.3.9 | Results of audits should include clinical, nursing and admin and are used to drive improved Healthrecords management practice throughout the Hospital | Ann Brennan |  | Quarter 8 2008 | Completed
33 | 27.10.09 | 9 | 9.3.4 | Plan in place to introduce computerised emergency department link to patient administration system | Ann Brennan
34 | 27.10.09 | 10 | 10.3.5 | New out-patients reception area to be designed to procect patient confidentiality | Ann Brennan |  | Quarter 04 2008 | Completed
35 | 27.10.09 | 10 | 10.3.5 | Ensure any plans for new buildings take into account the need for patient confidentiality. | Ann Brennan | Quarter 04 2011 |  | Not yet due
36 | 27.10.09 | 10 | 10.3.9 | Continue to educate staff on the awareness of how to deal with healthcare complaints. | Ann Brennan | Quarter 01 2010 |  | Not yet due
37 | 27.10.09 | 11 | 11.3.3 | Review existing structures of clinical staff participation in the validation of the coding process. | Ann Brennan | Quarter 01 2010 |  | Not yet due
38 | 2009-11-02 | 7 | 7.3.16 | Hospital decision not to implement this standard | Ann Brennan
39 | 2009-11-02 |  | 7.3.42 | Staff need further education on the necessity to counter sign all instructions via telephone | Frances Campbell
40 | 2009-11-02 |  | 7.3.59 | Direct access referal letters need date stamp on receipt. All other referral letters stamped | Ann Brennan
41 | 2009-11-02 |  | 7.3.6 | I.T.P system needs updating to include referral date recording | Cathal PrendergastQuarter 4 2010
42 | 2009-11-02 |  | 7.3.65 | Staff Assessment Policy to be given out to NCHD 's at induction on what to include on physical and history on admission | Ann Brennan | 01 2001 |  | Not yet due
43 | 2009-11-02 |  | 7.3.66 | as above | Ann Brennan | 01 2010 |  | Not yet due
44 | 2009-11-02 |  | 7.3.59 | OPD fully compliant. Date stamping at ward level needs enforcing. | Oliver Cunningham | Quarter 4 2009 |  | Not yet due
45 | 2009-11-02 | 7 |  | New Audit to be put in place based on standard 7 and reported on monthly | Ann Brennan | quarter 1 2010 |  | Not yet due
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
Note on F6: This date is entered automatically from the computer's system clock.

## HIQA QIP
HIQA National Standards for the Prevention and Control of Healthcare Associated Infection
| QIPs LOG FOR: |  |  | St Michaels Hospital Dunlaoghaire |  |  | QIPs STATUS
Enter name of hospital etc.
|  |  |  | TODAY'S DATE: | 2018-03-22 |  | Completed | 4
[7 empty] | Not yet due | 9
[7 empty] | Late | 0
Note: Please ensure you enter the 'Entry Date' (i.e. date that QIP is entered into the log), 'Due Date' (i.e. date that the
QIP is due for completion), and, when appropriate, the 'Completed Date' (i.e. date that QIP has been fully implemented).
Number | Entry Date | Standard | Criterion | Description of Quality Improvement Plan (QIP) | Responsible Person | Due Date | Completed Date | QIP Status | Comments
1 | 2018-03-22 | 2 | 2.6.1 | Continous and ongoing hospital painting programme | SM, KB | 31/09/2018 |  | Not yet due | This is an ongoing programme
2 | 2018-03-22 | 2 | 2.1 | IPC to be included in patient safety committee for Governance | SMC, AMG | 2017-09-29 | 2017-09-29 | Completed
3 | 2018-03-22 | 2 | 2.6.1 | Ongoing Sink and bathroom refurbishment programme | SM, KB | 2018-12-31 |  | Not yet due | This is an ongoing programme
4 | 2018-03-22 | 2 | 2.6.2 | Appropiate Medication storage in HDU | NPDC, MM | 2017-11-01 | 2017-11-01 | Completed
5 | 2018-03-22 | 2 | 2.3 | Update of IPC policies in line with National standards | AMG | 2018-12-31 |  | Not yet due
6 | 2018-03-22 | 2 | 2.6.1 | Improve clarity of IPC audit feedback | AMG | 2017-12-15 | 2017-12-15 | Completed
7 | 2018-03-22 | 2 | 2.6.1 | Isolation room risk assessment to be included in nursing admission | NPDC | 31/06/2018 |  | Not yet due
8 | 2018-03-22 | 2 | 2.6.1 | Reconfiguration of storage facilities in HDU | HDU | 2017-11-01 | 2017-11-01 | Completed
9 | 2018-03-22 | 2 | 2.6.3 | Ongoing Monitoring and promoting of hand hygiene pracitices | IPCT/NPDC | 2018-12-31 |  | Not yet due | This is an ongoing programme
10 | 2018-03-22 | 2 | 2.1 | Ongoing Monitoring of Quality Care Nursing Metrics | NPDC | 2018-12-31 |  | Not yet due
11 | 2018-03-22 | 2 | 2.5.1 | Continue Imlementation and auditing of infection control care bundles | IPCT | 2018-11-30 |  | Not yet due | This is an ongoing programme
12 | 2018-03-22 | 2 | 2.6.1 | Reconfiguration of patient facilities in HDU | SM, KB | 2018-12-31 |  | Not yet due
13 | 2018-03-22 | 2 | 2.6.1 | Continous improvement with patient equipment cleaning | AMG | 2018-12-31 |  | Not yet due
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
Note on F6: This date is entered automatically from the computer's system clock.